KATARSIS Network Meeting – I

Barcelona, 18-19 September 2006

These minutes (Abid, Frank) are minimalist, they only contain the discussion and decisions on deadlines and duties. With Diana around as of January, paradise will be reborn!

Day 2

Afternoon Session: Chair, Juan-Luis Klein

Methodology for KATARSIS – scientific and interactive

(Presented by: Frank Moulaert, Serena Vicari, Jean Hillier)

Discussion:

Juan-Luis:	How to integrate practitioners and user groups?

Frank: 		We will not do it at this stage. However, if Lead Partners deem it necessary, they can identify relevant groups etc at this point as well. We can bring both groups of users together at one of our next meetings (2008?)

Bas:		How to identify Exclusion Dynamics? What if we do not find relevant literature?

Frank:	Socially Creative Strategies are the main focus. We can always try to find practice examples.

Frank:

- Drafts for WP1.i should be ready by June 2007. This is necessary for quality control and subsequent Integration Exercises.

- There is an existing list in proposal of members of user groups. However, new user groups and members can also be identified.

- Coordinator will send a general message to user groups on the intended plan of 5-working days for the Integration Exercises to check their availabilities. On receiving feedback from users all information will be provided to LP. Later on LP will directly coordinate with respective user groups on the management of the IE.

Richard: 	For the examples of failed SC strategies, we will need to make judgements.

Laurent: 	For the 50 page report, at what stage do the SP contribute?

Frank:

- 1st part of the report is a survey of up to 25 pages.

- Utilisation of inputs from SP is the discretion of LP.

- Second part of the report to be more ‘technical’ (well organised focused inputs from different partners and users, as well as external experts)

- EF surveys will be put on KATARSIS website in the form of protected PDF documents, accessible only to the KATARSIS partners (and active users).

Laurent: 	To identify grassroots initiatives, language can be a barrier.

Frank: 		Most of the user groups identified until now can converse in English, but later on new communication modalities may have to be decided.

Montserrat: 	It is a multilingual forum, so all languages would be accommodated.

Isabel: 		What is contribution of SP?

Frank: 		First is to identify the field and questions for survey. Later on develop theoretical surveys.

Deadlines and duties:

Project start date: 1st May, 2007

| Dates | What? Activity- Output: | Who? | Additional |
| --- | --- | --- | --- |
| 22 October 2007 | Comments on WP1.i methodology | All but especially LP and SP of WP1.i | To be provided in E-written form to Frank |
| 22 October 2007 | 10 lines | All | Please write and deliver the 10 lines of comments for each intervention you made. |
| 7 November 2007 | Final methodology for WP1 | Coordination team | Should include template for D1.i |
| 7 November 2007 | Contact user-groups – Integration Exercises Calendar | Frank – Jean - Serena | Frank circulates draft letter in coordinating team |
| 7 November 2007 | Proposal for training initiatives (which programmes? When? Who? Where) | Serena | Serena circulates overview (PhD programmes, IP, guest lectures) |
| 1 March 2007 | Drafty drafts of all D1.i (i=1,...5) | All LP | Model in TA (updated) to be followed |
| 29-31 March 2007 | Roskilde Workshop: WP1 presentations and discussions – Methodology WP2 etc. | John A – Coordinating team (Diana included) | 28th Travel day 29th Trips to user groups 30-31 Working days 1st April Travel back |
| 30 April 2007 | First Reporting Period ends |  |  |
| 15 May 2007 | All send individual activity reports and financial documents & forms to Newcastle | Diana Maccallum and Kim McCartney coordinate | All complete online questionnaires and send copies to Newcastle |
| 30 May 2007 | Newcastle submits Activity & Management Reports to Commission | Diana and Frank coordinate | Official EC models to be followed |
| 30 July 2007 | Drafts reports of D1.i for distribution |  | LP of each WP1.i are in charge |
| 30 Oct 2007 | Deliverables D1.i due to Commission | Frank/Jean/Diana | Model of presentation to be followed |
| 28 Jan – 1 Feb, 2008 | Workshops 3,4, and 5: Integration Exercises WP2, 3, 4 – Location to be negotiated. | Coordinating team (Jean leads) | Travel days to be added. First day is reserved for local workshops. |
| 30 April 2008 | Second Reporting Period ends |  |  |